## Sheet1
Task | Start Date | Day to Complete
Analysis of requirement | 2018-01-02 | 10
Making abstract or prototype | 2018-01-12 | 12
Design wireframe | 2018-01-25 | 21
Implement project with database | 2018-02-16 | 16
Software Testing | 2018-03-02 | 9
Analysing issues or feedback | 2018-03-12 | 3
Changes according to feedback | 2018-03-16 | 9